## Block Details
S.N. | Block | Regime | Round | Category | Basin | Basin category | State | District(s) | Block Area |  |  | RSC signing date | Current Status (Active/ Rel) | Current Stage | Relinquishment date
[9 empty] | Original | Revised | Date of Revision
1 | MN-ONHP-2018/1 | OALP | II | Combination (Onland + Offshore) | Mahanadi | II | Odisha | Cuttak, Khorda, Jagatsinghpur, Puri, Kendrapada | 2933.85 | NA |  | 16.07.2019 | Active | Exploration
2 | MN-ONHP-2018/2 | OALP | II | Onland | Mahanadi | II | Odisha | Khorda, Puri | 2539.51 | NA |  | 16.07.2019 | Active | Exploration
3 | MN-ONHP-2018/3 | OALP | II | Onland | Mahanadi | II | Odisha | Kendrapada, Jajpur, Bhadrak, Balasore | 3138.59 | 3097.12 |  | 16.07.2019 | Active | Exploration
4 | MN-ONHP-2018/4 | OALP | III | Onland | Mahanadi | II | Odisha | Kendujhar, Balasore, Mayurbhanj, Bhadrak, Jajpur, Kendrapada | 3196.86 | 2874.52 |  | 16.07.2019 | Relinquished | Relinquished | 28.02.2025
5 | MN-ONHP-2018/5 | OALP | III | Onland | Mahanadi | II | Odisha | Cuttack, Jajpur, Jagatsinghpur, Kendrapada , Dhenkanal | 2299.74 | NA |  | 16.07.2019 | Active | Exploration
6 | MN-UDWHP-2023/2 | OALP | IX | Ultra Deep Water | Mahanadi | II | Offshore | NA | 9425.84 | NA |  | 15.04.2025 | Active | Exploration
7 | MN-UDWHP-2023/3 | OALP | IX | Ultra Deep Water | Mahanadi | II | Offshore | NA | 9831.48 | NA |  | 15.04.2025 | Active | Exploration
8 | KG-UDWHP-2023/1 | OALP | IX | Ultra Deep Water | Krishna Godavari | I | Offshore | NA | 9495.16 | NA |  | 15.04.2025 | Active | Exploration
9 | KG-UDWHP-2023/2 | OALP | IX | Ultra Deep Water | Krishna Godavari | I | Offshore | NA | 9223.22 | NA |  | 15.04.2025 | Active | Exploration

## PEL _PML_PL validity
S.N. | Block | PEL/ PL granting authority | Initial PEL/ PL grant date | Effective/ Commencement Date | PEL to PL converted | Current PEL/ PL validity | Current year of PEL/ PL | Last year rate of PEL fees/ Lease Rent | Last year amount of PEL fees/ Lease Rent
1 | MN-ONHP-2018/1 | State/ Central | 27.07.2020/ 30.08.2019 | 27.07.2020 | Yes | 26.07.2027 | 1st | 2000 | 5867700
2 | MN-ONHP-2018/2 | State Govt. | 27.07.2020 | 27.07.2020 | Yes | 26.07.2027 | 1st | 2000 | 5079020
3 | MN-ONHP-2018/3 | State Govt. | 09.03.2021 | 09.03.2021 | Yes | 08.03.2027 | 1st | 2000 | 6194240
4 | MN-ONHP-2018/4 | State Govt. | 09.03.2021 | 09.03.2021 | No | 08.03.2025 | NA | NA | NA
5 | MN-ONHP-2018/5 | State Govt. | 22.07.2020 | 22.07.2020 | Yes | 21.07.2027 | 1st | 2000 | 4599480
6 | MN-UDWHP-2023/2 | Central Govt. | 23.12.2025 | 20.01.2026 | NA | 22.12.2055 | 1st | 2000 | 18851680
7 | MN-UDWHP-2023/3 | Central Govt. | 23.12.2025 | 20.01.2026 | NA | 22.12.2055 | 1st | 2000 | 19662960
8 | KG-UDWHP-2023/1 | Central Govt. | 23.12.2025 | 20.01.2026 | NA | 22.12.2055 | 1st | 2000 | 18990320
9 | KG-UDWHP-2023/2 | Central Govt. | 23.12.2025 | 20.01.2026 | NA | 22.12.2055 | 1st | 2000 | 18446440

## CWP details
S.N. | Block | Committed Work Program (CWP) |  |  | Achievement |  |  | Additional Work |  |  | Under drilling (nos.) | Location under drilling | Current drilled Depth (m) | TD (m) | Percentage completion
|  | 2D (LKM) | 3D (Sq. Km.) | Wells | 2D (LKM) | 3D (Sq. Km.) | Wells | 2D (LKM) | 3D (Sq. Km.) | Wells
1 | MN-ONHP-2018/1 | 200 | 350 | 5 | 242 | 350 | 1 | 0 | 176 | 0 | 0
2 | MN-ONHP-2018/2 | 500 | 260 | 3 | 502.6 | 314.5 | 3 | 0 | 0 | 0 | 0
3 | MN-ONHP-2018/3 | 0 | 330 | 3 | 0 | 345 | 0 | 0 | 154 | 0 | 1 | OBKB-R | 2000 | 3393 | 58.94%
4 | MN-ONHP-2018/4 | 0 | 330 | 3 | 0 | 330 | 0 | 0 | 0 | 0 | 0
5 | MN-ONHP-2018/5 | 760 | 400 | 6 | 760 | 442 | 3 | 0 | 0 | 0 | 0
6 | MN-UDWHP-2023/2 | 1101 | 2000 | 0 | 1101.45 | 2003.7 | 0
7 | MN-UDWHP-2023/3 | 1000 | 500 | 0 | 1000.85 | 500.71 | 0
8 | KG-UDWHP-2023/1 | 1000 | 1200 | 0 | 1000.25 | 1200 | 0
9 | KG-UDWHP-2023/2 | 1101 | 1600 | 0 | 1101.1 | 1601.88 | 0
1101000
2400000
3501000

## Location inventory
S.N. | Block | Number of Locations released till date | Details (Name and TD) | Primary/ Secondary targets | EDPMB No. | EDPMB Date | Whether already drilled | Drilled wells |  |  | To be drilled
[8 empty] | Actual drilled depth | Key findings | Studies carried out | EDS | Planned completion date | Current status
1 | MN-ONHP-2018/1 | 2 | OBRA : 1460 m, OBRD: 1500 m | OBRA: Clastics/carbonates within paleocene OBRD: Mesozoic castics & Early Cretaceous | OBRA: 34 OBRD: 49 | OBRA: 31.0.2023 OBRD: 08.05.2026 | OBRA: Drilled OBRD: Not drilled | OBRA: 1460 m | OBRA: Dry | Biostratigraphic Study | OBRD: June 2027 | OBRD: July 2027 | OBRD: Estimates under preparation
2 | MN-ONHP-2018/2 | 5 | OPUE: 1080 m, OPUB: 2004 m, OPUH: 1500 m, OPUF: 1600 m. OPUC: 3130 m | OPUE: Mesozoic clastic within early creataceous OPUB: Mesozoic Clastics within Early Cretaceous OPUH: Paleocene Sand OPUF: Mesozoic clastic within early creataceous OPUC: Mesozoic clastic within early creataceous | OPUE: 21 OPUB: 21 OPUH: 38 OPUF : 36 OPUC: 20 | OPUE: 25.01.2022 OPUB: 25.01.2022 OPUH: 20.08.2024 OPUF: 09.05.2024 OPUC: 11.10.2021 | OPUE: Drilled OPUB: Drilled OPUH: Drilled OPUF: Not drilled OPUC: Not drilled | OPUE: 1080 m OPUB: 2004 m OPUH: 1500 m | OPUE: Dry OPUB: Dry OPUH: Dry |  | OPUF: Mid Nov. 2026 OPUC: | OPUF: Dec. 2026 OPUC: | OPUF: Civil work completed OPUC: Land Acquisition through IDCO in progress
3 | MN-ONHP-2018/3 | 2 | OBKB-R: 3393 m, OBKF: 2600 m | OBKB-R: Mesozoic clastic within early creataceous OBKF: Mesozoic clastic within early creataceous | OBKB-R: 34 OBKF: 49 | OBKB-R:31.10.2023 OBKF: 08.05.2026 | OBKB-R: Under drilling OBKF: Not drilled | OBKB-R: Under drilling | OBKB-R: Under drilling |  | OBKF: Aug 2027 | OBKF: Dec 2027 | OBKF: Civil survey in progress
4 | MN-ONHP-2018/4 | 0
5 | MN-ONHP-2018/5 | 3 | OCUB: 1040 m, OCUD: 3201 m. OCUH: 3747 m | OCUB: Early Cretaceous OCUD: Early Cretaceous OCUH: Early Cretaceous | OCUB: 23 OCUD: 28 OCUH: 28 | OCUB: 15.06.2022 OCUD: 30.01.2023 OCUH: 30.01.2023 | OCUB: Drilled OCUD: Drilled OCUH: Drilled | OCUB: 1040 m OCUD: 3201 m OCUH: 3747 m | OCUB: Dry OCUD: Not tested OCUH: Not tested (Thermogenic gas while N/down BOP) | OCUH: Biostratigraphic Study
6 | MN-UDWHP-2023/2 | 0
7 | MN-UDWHP-2023/3 | 0
8 | KG-UDWHP-2023/1 | 0
9 | KG-UDWHP-2023/2 | 0

## Timeline details
S.N. | Block | OALP Bid Round | Contractual Structure | Ideal Contractual Timelines |  |  |  | Current Phase of the Block | IEP/ Phase-I/ EP timelines |  |  |  |  | SEP/ Phase-II timelines
|  |  |  | IEP/ Phase-I/ EP | Permissible extensions | SEP/ Phase-II | Permissible extensions |  | IEP start date | IEP/ Phase-I/ EP validity (contractual) | Extensions granted | IEP validity (current) | Whether policy dated 11.11.25 availed | SEP start date | SEP validity (contractual) | Extensions granted | SEP validity (revised)
1 | MN-ONHP-2018/1 | II | IEP+SEP | 3 years | 1 year | 3 years | 1 year | IEP | 27.07.2020 | 26.07.2023 | 1. 1 year as per Article 3.4 (a) 2. 217 days of Force Majeure due to COVID | 22.08.2025 | Yes; applied for 2 quarters
2 | MN-ONHP-2018/2 | II | IEP+SEP | 3 years | 1 year | 3 years | 1 year | IEP | 27.07.2020 | 26.07.2023 | 1. 1 year as per Article 3.4 (a) 2. 217 days of Force Majeure due to COVID | 22.08.2025 | Yes; applied for 1 quarter
3 | MN-ONHP-2018/3 | II | IEP+SEP | 3 years | 1 year | 3 years | 1 year | IEP | 09.03.2021 | 08.03.2024 | 1 year as per Article 3.4 (a) | 08.03.2025 | Yes; applied for 2 quarters
4 | MN-ONHP-2018/4 | III | IEP+SEP | 3 years | 1 year | 3 years | 1 year | Relinquished | 09.03.2021 | 08.03.2024 | 1 year as per Article 3.4 (a) | 08.03.2025
5 | MN-ONHP-2018/5 | III | IEP+SEP | 3 years | 1 year | 3 years | 1 year | IEP | 22.07.2020 | 21.07.2023 | 1. 1 year as per Article 3.4 (a) 2. 222 days of Force Majeure due to COVID | 22.08.2025 | Yes; applied for 2 quarters
6 | MN-UDWHP-2023/2 | IX | Phase-I + Phase-II | 3 years | 18 months | 4 years | 0 | Phase-I | 20.01.2026 | 19.01.2029 |  | 19.01.2029 | NA
7 | MN-UDWHP-2023/3 | IX | Phase-I + Phase-II | 3 years | 18 months | 4 years | 0 | Phase-I | 20.01.2026 | 19.01.2029 |  | 19.01.2029 | NA
8 | KG-UDWHP-2023/1 | IX | Single Phase | 4 years | 18 months | NA | NA | EP | 20.01.2026 | 19.01.2030 |  | 19.01.2030 | NA
9 | KG-UDWHP-2023/2 | IX | Single Phase | 4 years | 18 months | NA | NA | EP | 20.01.2026 | 19.01.2030 |  | 19.01.2030 | NA

## BG details
S.N. | Block | Current Phase of the Block | Amount of BG submitted (USD) | Amount of BG submitted (INR) | BG validity till | BG calim date | BG renewal timeline (as per RSC)
1 | MN-ONHP-2018/1 | IEP | 8500000 | 807245850 | 28.02.2027 | 29.04.2027 | 10 days prior to expiry
2 | MN-ONHP-2018/2 | IEP | 5750000 | 546078075 | 28.02.2027 | 29.04.2027 | 10 days prior to expiry
3 | MN-ONHP-2018/3 | IEP | 5750000 | 546078075 | 08.03.2027 | 07.05.2027 | 10 days prior to expiry
4 | MN-ONHP-2018/4 | Relinquished
5 | MN-ONHP-2018/5 | IEP | 10400000 | 987689040 | 28.02.2027 | 29.04.2027 | 10 days prior to expiry
6 | MN-UDWHP-2023/2 | Phase-I | 4101000 | 346827722 | 14.04.2028 | 13.06.2028 | 10 days prior to expiry
7 | MN-UDWHP-2023/3 | Phase-I | 1750000 | 148000125 | 14.04.2028 | 13.06.2028 | 10 days prior to expiry
8 | KG-UDWHP-2023/1 | EP | 2800000 | 236800200 | 14.04.2029 | 13.06.2029 | 10 days prior to expiry
9 | KG-UDWHP-2023/2 | EP | 3501000 | 296084822 | 14.04.2029 | 13.06.2029 | 10 days prior to expiry

## Investment details
S.N. | Block | Investment Made (INR) |  |  |  | Liquidated Damages (LD) paid |  |  |  |  | Paid extensions availed |  |  | Total outgo (INR)
|  | Seismic | Wells | Others | Total | Seismic (Mill USD) | Wells (Mill USD) | Others (Mill USD) | Total (Mill USD) | Total ( Cr INR) | Quarters | Amount (USD) | Amount (INR)
1 | MN-ONHP-2018/1 |  |  |  |  | 0 | 6.25 | 0 | 6.25 | 53.634 | 2 | 50000
2 | MN-ONHP-2018/2 |  |  |  |  | 0 | 1.25 | 0 | 1.25 | 10.68 | 1 | 25000
3 | MN-ONHP-2018/3 |  |  |  |  | 0 | 3.75 | 0 | 3.75 | 31.71 | 2 | 50000
4 | MN-ONHP-2018/4 |  |  |  |  | 0 |  | 0
5 | MN-ONHP-2018/5 |  |  |  |  | 0 | 5 | 0 | 5 | 42.908 | 2 | 50000
6 | MN-UDWHP-2023/2
7 | MN-UDWHP-2023/3
8 | KG-UDWHP-2023/1
9 | KG-UDWHP-2023/2

## MC meeting details
S.N. | Block | No. of MC meetings held | Dates of MCRs
1 | MN-ONHP-2018/1 | 6 | i) 1st- 15.09.2020 ii) 2nd- 15.06.2021 iii) 3rd- 18.01.2022 iv) 4th- 18.04.2023 v) 5th- 16.01.2024 vi) 6th- 19.12.2024
2 | MN-ONHP-2018/2 | 6 | i) 1st- 15.09.2020 ii) 2nd- 15.06.2021 iii) 3rd- 18.01.2022 iv) 4th- 18.04.2023 v) 5th- 16.01.2024 vi) 6th- 10.12.2024
3 | MN-ONHP-2018/3 | 5 | i) 1st- 15.06.2021 ii) 2nd- 18.01.2022 iii) 3rd- 18.04.2023 iv) 4th- 16.01.2024 v) 5th- 09.12.2024
4 | MN-ONHP-2018/4
5 | MN-ONHP-2018/5 | 7 | i) 1st- 15.09.2020 ii) 2nd- 15.06.2021 iii) 3rd- 18.01.2022 iv) 4th- v) 5th- 09.11.2023 vi) 6th- 16.10.2024 vii) 7th- 12.08.2025
6 | MN-UDWHP-2023/2 | 0
7 | MN-UDWHP-2023/3 | 0
8 | KG-UDWHP-2023/1 | 0
9 | KG-UDWHP-2023/2 | 0

## Backup Database
Basins
Mumbai Offshore
Krishna Godavari
Assam Shelf
Assam Arakan Fold Belt
Rajasthan
Cauvery
Cambay
Kutch
Mahanadi
Andaman Nicobar
Vindhyan
Himalayan Foreland/ Ganga/ Punjab
Kerala Konakan
Bengal Purnea
Saurashtra
Pranhita Godavari

## Statutory clearances
Project | Block | Location | EC Applied On | EC Received On | Validity of EC | CTE Applied On | CTE Received On | Validity of CTE | CTO Applied On | CTO Received On | Validity of CTO | Remarks
Mahanadi Basin Project | MN-ONHP-2018/1 | OBRA | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 05.08.2025 | 24.11.2025 | 23.11.2030 | 24.02.2026 | 31.03.2026 | 31.03.2026
Mahanadi Basin Project | MN-ONHP-2018/2 | OPUB & OPUH | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 29/08/2022 | 25/11/2022 | up to 24.11.2027 | 06/01/2023 | 26/05/2023 | 31.03.2025 | Abandoned
Mahanadi Basin Project | MN-ONHP-2018/2 | OPUC | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | Applied, however pending due to land acquisition |  | NA | Not applied |  | NA | Land Acquisition is in process
Mahanadi Basin Project | MN-ONHP-2018/2 | OPUE | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 29/08/2022 | 25/11/2022 | up to 24.11.2027 | 16/05/2023 | 26/05/2023 | 31.03.2024 | Abandoned
Mahanadi Basin Project | MN-ONHP-2018/2 | OPUF | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | Not applied |  | NA | Not applied |  | NA | Civil Work is completed
Mahanadi Basin Project | MN-ONHP-2018/3 | OKBK / OKBK-R | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 10/09/2024 | 01/01/2025 | up to 31.12.2029 | 06/05/2025 | 24/06/2025 | 31.03.2027 | CTO renewal date 04.04.2026 and validity of CTO is upto 31.03.2027.
Mahanadi Basin Project | MN-ONHP-2018/4 | NIL | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | NA | NA | NA | NA | NA | NA | This location is relinquished.
Mahanadi Basin Project | MN-ONHP-2018/5 | OCUB | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 29/08/2022 | 19/07/2023 | up to 18.07.2028 | 16/10/2023 | 16/11/2023 | 31.03.2024 | Abandoned
Mahanadi Basin Project | MN-ONHP-2018/5 | OCUD | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 13/02/2024 | 27/06/2024 | up to 26.06.2029 | 25/06/2024 | 12/07/2024 | 31.03.2025 | Abandoned
Mahanadi Basin Project | MN-ONHP-2018/5 | OCUH | 11.09.2020 | 01.02.2021 | up to 31.01.2028 | 13/02/2024 | 27/06/2024 | up to 26.06.2029 | 25/06/2024 | 31.03.2025 | 31.03.2026 | CTO renewal date 31.03.2025 and validity of CTO is upto 31.03.2026.