## RSC Compliance Register
Compliance ID | Broad Compliance Head | Compliance / Obligation | Article / Clause | Trigger | Timeline / Frequency | Compliance Type | Responsible Department | Nodal Officer | Approving Authority | Alert (Days Before) | Status | Supporting Documents | Remarks
CA-01 | Contract Administration | Bank Guarantees | Art.27 |  | As applicable | One-time |  |  |  | 30
CA-02 | Contract Administration | Operator/JOA/Assignment approvals |  | Event | As applicable | Event |  |  |  | 30
EP-01 | Exploration Phase | Committed Work Programme completion | Art.5 | Contract Effective Date | Per RSC | Milestone |  |  |  | 90
EP-02 | Exploration Phase | Exploration period extension |  | Before expiry | Per RSC | Event |  |  |  | 90
EP-03 | Exploration Phase | Relinquishment notice |  | Before phase expiry | Per RSC | Event |  |  |  | 90
DA-01 | Discovery & Appraisal | Notification of Discovery (NOD) | Art.10 | Discovery | Within stipulated period | Event |  |  |  | 30
DA-02 | Discovery & Appraisal | PCI Notice | Art.10 | Potential commercial discovery | Per RSC | Event |  |  |  | 30
DA-03 | Discovery & Appraisal | Appraisal Programme submission | Art.10 | After discovery | Per RSC | Event |  |  |  | 60
DP-01 | Development & Production | Field Development Plan (FDP) | Art.10 | Appraisal complete | Per RSC | Event |  |  |  | 90
DP-02 | Development & Production | Annual Production Programme | Art.10 | Annual | Yearly | Recurring |  |  |  | 30
MC-01 | Management Committee | MC Meeting | Art.6 |  | Half-yearly/As required | Recurring |  |  |  | 15
MC-02 | Management Committee | Agenda & Minutes |  | Before/After meeting | Per procedure | Recurring |  |  |  | 7
RR-01 | Reporting | Monthly Revenue Statement | Art.23 | Monthly | Monthly | Recurring |  |  |  | 5
RR-02 | Reporting | Annual Audit Report | Art.23 | FY End | Annual | Recurring |  |  |  | 30
RF-01 | Revenue & Finance | Revenue Share payment | Art.15 | Monthly | Monthly | Recurring |  |  |  | 5
RF-02 | Revenue & Finance | Royalty payment | Art.16 | Monthly | Monthly | Recurring |  |  |  | 5
ENV-01 | Environment & HSE | Environmental Clearance compliance | Art.14 | Project lifecycle | Continuous | Continuous |  |  |  | 30
ENV-02 | Environment & HSE | Emergency Response Plan | Art.14 | Before drilling | Periodic review | Recurring |  |  |  | 30
ENV-03 | Environment & HSE | Site Restoration Fund | Art.14 | Annual | Annual | Recurring |  |  |  | 30
TD-01 | Technical Data | Submission of technical data/reports | Art.24 | As generated | Periodic | Recurring |  |  |  | 15
TD-02 | Technical Data | Maintain confidentiality | Art.24 | Continuous | Continuous | Continuous
MP-01 | Measurement | Meter calibration & production measurement | Art.13 | As scheduled | Periodic | Recurring |  |  |  | 15
LC-01 | Local Content | Indian manpower & training obligations | Art.20 | Annual | Annual | Recurring |  |  |  | 30
INS-01 | Insurance | Insurance coverage renewal | Art.22 | Before expiry | Annual | Recurring |  |  |  | 30
DS-01 | Domestic Supply | Domestic supply/sales obligations | Art.17 | As applicable | Continuous | Continuous
PL-01 | Lease & Licensing | Lease application/extension | Art.11 | Event | Per RSC | Event |  |  |  | 90
JD-01 | Joint Development | Joint development/common infrastructure | Art.18 | As applicable | Event | Event |  |  |  | 30
CC-01 | Contract Closure | Abandonment/Site Restoration/Closure | Art.4 & 14 | Termination | Per RSC | Event |  |  |  | 180